## Buvidal Project Plan
BACKGROUND The following project planner has been designed to support drug treatment providers in mapping out and completing the relevant activities in order to implement Buvidal® prolonged release buprenorphine solution for injection into their local opioid dependence treatment systems. Please note, this project planner serves as a guide and cannot include all the specific local requirements that may need to be fulfilled. Some activities listed below and the sequence in which they are listed may be irrelevant depending on the organisation. Therefore, users are encouraged to make amendments to reflect their organisation’s individual requirements. It often helps to identify and engage with wider system stakeholders to ensure awareness of Buvidal and enable continuity of care.
| Camurus Template UK-BUV-2400238, Feb 2025 | For Prescribing Information and Adverse Event reporting click here
This row contains headers for the project schedule that follows below them. Navigate from B8 to BK8 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell H8 and continues to cell BK8. All project timeline charting is auto-generated based on the category, start date and number of days entered in the Milestones table. | Task | Considerations (please hover pointer over right side of panel for suggestions) | Step needed locally? | Owner | Task start date | Task due date | Complete | RAG rating | Comments / Update/s
Enter Project information starting in cell B10 to cell F10. Enter Milestone Description, select a Category from the drop-down list, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Engagement and buy-in from stakeholders
| Proposal to introduce / implement Buprenorphine LA Injection discussed with Regional Manager/Commissioning team / Local delivery board to understand funding and capacity. | F
If required, provider/commissioner develops proposal and business case for implementing buprenorphine LA injection, including the financial impact and potential number and types of patients to receive buprenorphine LA injection and matched to clinical capacity to deliver the intervention
Establish Buprenorphine LA Injection implementation lead and/or multi-disciplinary working group with clinical and non-clinical representation
Prison Senior Management Team (SMT) to be briefed and understand potential operational impacts of implementation.
Commitment received from Governor to support implementation strategy
Prison substance misuse startegy lead invited to implementation planning group
Substance misuse team and service user engagement meetings/events including other stakeholders e.g. healthcare team, prison staff, prison Medicines Management Committee (MMC), and community substance misuse service engagement
Consult with relevant Pharmacy Lead and establish Controlled Drug (CD) license status of premises and to decide on Buvidal dispensing/delivery model i.e. *Onsite, Buddy pharmacy or Pharmacist administration
Onsite storage & supply: • ensure that CD cabinet(s) meet regulatory and legal requirements • apply for/ renew a Home Office licence if one isn’t already in place
Utilise / Develop staff (prison and healthcare) information sheets/leaflets – role of staff (prison/health), how/when/risks/what to look out for
Develop service user information sheets/ leaflets/posters around for who, how and when buprenorphine LA injection might be used
Develop communications plan for all relevant stakeholder groups
Liaise with community treatment services to ensure they are aware of the service being provided. Develop pathway following release of patients.
Ensure access to Alliance, order initial stock.
To add more data, Insert new rows ABOVE this one
Formulary approval
Agree the clinician who will support the buprenorphine LA injection formulary submission to the prison MMC and provider governance arrangements if needed
Supporting clinician collates evidence required for the formulary submission (as per local formulary addition guidelines/process)
Buprenorphine LA injection submission presented and approved at a relevant meeting (may commonly be referred to as prison MMC, drugs and therapeutic drugs and therapeutic committee meetings, formulary meetings, medicines management meetings, LDB etc)
To add more data, Insert new rows ABOVE this one
Staff training and clinical protocol development
Standard Operating Procedures (SOPs): Develop and authorise local SOPs for the service
Clinical governance group or prison MMC agrees what treatment protocol should cover and how implementation and outcomes will be monitored (to include relevant prison enabling/monitoring)
Develop a training plan for all relevant staff All relevant staff receive training: (1) buprenorphine LA injection presentation (safety profile and efficacy), (2) injection administration including video demonstration, (3) familiarisation with supporting materials, i.e. dosing card, patient/ Healthcare Professional (HCP) information booklets, quick injection guide, (4) management of missed doses (5) read and understand SOPs, (6) custodial staff awareness and support training including information packs, (7) peer support training
All relevant staff receive training: (1) Buprenorphine LA Injection presentation (safety profile and efficacy), (2) Buprenorphine LA Injection administration including video demonstration and practice using demonstration devices (3) familiarisation with supporting materials i.e. patient information booklets, patient alert card, HCP information booklet, dosing card, quick injection guide
Bespoke prescriber training, SMS prescribers + other healthcare prescribers, GP’s etc
Clinical protocol development: DTS determine their patient selection criteria
Clinical protocol development: DTS finalise their clinical protocol and other relevant SOPs
enter Project information starting in cell B10 to cell F10. Enter Milestone Description, select a Category from the drop-down list, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Clinical protocol development: documentation is signed of by relevant clinician/team
Camurus on going support around workforce training, new starter induction etc
To add more data, Insert new rows ABOVE this one
Initiating Buvidal
Prison Substance Misuse Team/clinicians identify patients on their caseloads using the agreed patient selection criteria and agree these with prescribers. Consider liaising with prison service to enable shared care and risk management
Suitable patients are invited into a session where they are informed about Buprenorphine LA Injection
Consideration of buprenorphine LA injection as an option for OST is included as part of usual service engagement, clinical assessment or review for OST and included in information about the access to and engagement with OST services in the prison
Patients agreed to commence Buprenorphine LA Injection are booked in to see the prescribing clinicians and psychosocial team
Prescribers liaise with their pharmacy service provider to ensure that the correct dose/strength preparations of buprenorphine LA injection are ordered in advance of commencing treatment
Liaison with wider teams, including prison and probation staff to ensure adequate facilities and processes in place to establish smooth initiation of services. Consider operational model required
Patients to be booked in for prescribing review
Preparing the patient – from medication point of view, need to be in mild withdrawal (peer support) but also meaningful use of time once on injection
LAB considered at all stages of treatment, medical reviews, keyworker discussion, change in pt circumstances
Consideration around DRU’s/ ISFL’s and how Buprenorphine LA Injection could be incorporated into this pathway
To add more data, Insert new rows ABOVE this one
This is an empty row | Using buprenorphine LA injection in regular clinical practice
If seeing people less frequently (i.e. as the patient is no longer collecting OST daily), ensure that access to psychosocial interventions, clinical review and recovery support is maintained, especially at the early stages of prescribing when the opportunities for change can be greatest
Develop effective tools to collate quantitative and qualitative review and feedback alongside data monitoring that feeds into the governance group to drive service improvement (see stage 3)
Liaison with wider staffing teams, including prison and probation staff to successfully monitor operational service outcomes and staff engagement
Planned releases and transfers: Release and transfer planning and links with post-release community services should commence several weeks before release. This allows planning for treatment changes pre-release, continuity of care, links with probation teams and pre-release dose schedules
*Onsite model: Storage and administration at the DTS This model can be considered provided the DTS has the required infrastructure e.g. a CD License or Registered Pharmacy (RP) status and can therefore stock Buvidal onsite, prescribing the medication to patients that they deem suitable. Pharmacist administration model Local Pharmacist(s) are identified who will administer Buvidal in a Pharmacy in the same way they administer other opioid substitution treatment. This will require a tariff to be paid to the Pharmacist.
Unplanned releases: urgent follow up processes and information sharing in place with probation and receiving community services/prison service including any minimum time frames for the next dose at point of release.
Upon discharge from prison setting, patient has the information needed to access next dose and community services, prison probation teams support engagement with community Substance Misuse Teams to ensure continuity of treatment.
Service evaluation - Future benefits, system cost and efficiency
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As more patients gain access to long acting Buprenorphine, services should consider transfers from community services and prisons. Ensuring continuity of care should be prioritised where possible.
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider clinics/staffing/operational support to enable delivery of service
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider incorporation into the establishment substance misuse strategy plan, set as standard agenda item on the strategy meetings to ensure good communication of project progress.
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If opting for on-site model:- is a HO Licence required? is there a CD cabinet in place? is there an account with Alliance Healthcare in place? If opting for a buddy pharmacy model:- is there a CD cabinet in place? If opting for a Pharmacist administration model:- budget holder to agree tariff/contract with Pharmacist/s. does a Patient Specific Directive (PSD) need to be developed? what about indemnity insurance?
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agree structure to support project governance and oversight
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agree what information would be helpful to share? when? with who? how often? E.g. overview, plan for implementation including timescales, progress updates,
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Send community providers letter of intent, consider joint training sessions.
Note on C19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Medicine ordering service
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Which committee/s? What documentation is required? When does documentation need to be submitted and to who? When are submissions reviewed? Is someone able to/required to attend the committee meeting to present the case/respond to questions
Note on C30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Clinical staff - prescribers, nurses, pharmacists Non-clinical staff - operational/service manager, psychosocial team, prescribing administration Additional staff in secure environments - mental health team, justice team, on-call team, drug strategy lead, relevant governor
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For secure environments:- Is medical hold necessary/appropriate?
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Clinic rooms? Clinic time? Staff availability? Are computer system updates/changes required/helpful? If buddy pharmacy model is planned;- how will patient consent to medication being collected on their behalf be captured? how will prescriptions be delivered and collected from the pharmacy?
Note on C34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are there any other committees/management teams that need to be aware of protocol?

## Lessons learned from HMP Holme (hidden)
Themes | Lessons learned from HMP Holme House interim review
Competent Prescriber | We had a GP prescriber who was invested, interested and keen to explore PRB as a treatment. He collaborated and sought support from other prescribers who had experience of the medication. With the support of the Camurus team, this ensured we were as prepared as we could be for initiating people onto the medication. The role of the GP is so important. They need to not only understand how to administer the medication but also communicate what was happening to the patient and reassure them as they transitioned from there current medication. The GP needed to understand dose optimisation using the injection as well as oral buprenorphine.
Supportive Nursing Team | This was a critical component (we learned). Prisoners on PRB often felt anxious as they stabilised on the medication. Often patients reported feeling some withdrawal symptoms as they stabilised (maybe real or psychosomatic – but nevertheless were a REAL issue) and our clinical nursing team spent many hours (daily contact in the first few weeks) as the patients stabilised on this medication. This therapeutic support and the relationship/alliance should NEVER be underestimated. It’s a vital support role and one our team excelled at. Often you think on a weekly injection there would be less work for the nursing staff… but for the first few weeks this isn’t the case.
Psychosocial Support | Alongside the nursing team, the recovery support workers in the psychosocial service also have an important role to play. Supporting prisoners to adopt new behaviours, in this case not having daily pick ups at the medicine administration point, often meant they extra support via meaningful activities was necessary to help people transition to a new way of being. This is where mutual aid and peer support facilitation provide excellent support opportunities. Plus cognitive behaviour therapy or other psychologically based interventions to help develop new skills to promote individual and social recovery (family and friends). This is about building recovery capital.
Involvement of other services | Closer working with mental health services and wider rehabilitation services within the prison is essential. Prisoners on PRB often report greater wellbeing and clarity of thought. This provides a great opportunity to explore reasons for drug use and address these – things like pain or trauma… new interventions such as EMDR or DBT delivered by the MH service can help a lot. It all makes a contribution to building someone's recovery capital – understanding the person behind the behaviour and addressing some of the root causes of their addiction rather than merely managing symptomatic relief.
Staff awareness | Generic education and awareness raising of health and prison officers via signage, posters, bulletins, videos, morning meetings, updates from the psychosocial team were embedded into our approach and we learned that you needed to deliver these key messages regularly and consistently in order to get those that needed to know aware of what was happening within the prison.
Lived experience involvement | We have already mentioned this and I discuss it again, having people with lived experience involved in the recovery support services and initiatives related to PRB is so important. Peer support working alongside professional services is a critical factor in the support services we deliver. Establishing Buvidal Champions, where people can share their experiences of PRB, can help demonstrate effectiveness and nurture hope. Holme House are working to have a Buvidal Champion on every residential unit as part of the mentors / peer support network.
Promotional materials available | Promotional materials available – a range of materials have been produced both by Camurus and prisons. These need to be informative as well as accessible. Many of the original materials needed to be adapted for the prison population who have neurodiversity traits and require extra help to understand this medicine. Materials should be produced in multiple formats – written, spoken, video and displayed via various channels – posters, TV as well as word of mouth.
Continuity of care | Pathways between prison and the community to support resettlement and reintegration need to be established and clearly promoted. Also prison to prison transfer pathways. All pathways in this respect designed to strengthen continuity of care. Its vital that once someone is stabilised on PRB that we mitigate any challenges / barriers they may face which could disrupt and destabilise their treatment. Holme House has a Reconnect Service which supports prisoners released as they resettle back in the community – often working with him in the weeks prior to and after release. They contact community services to ensure continued prescribing after release.
Prison to community pathway alignment | There are many stakeholders contributing to continuity of care. Examples include Area Prescribing Committees, Local Authority services commissioners, NHS England, OHID, PCC Offices… all of whom need to understand the needs of the person on PRB and how the wider systems can be configured to support rather than undermine continuity of care. This involved LA commissioning community services to prescribe PRB, getting budgets to do so, and then having the APC update community formularies to ensure prescribers could use the medication.
Prison Drug Strategy Leads and Health and Justice Co-ordinators | These roles have a supportive role to play in PRB administration. All prisoners are released on license. So Probation Practitioners need to know what medication the person is on. H&J Co-ordionator will help raise awareness and understanding of this area. Also as we establish Combatting Drugs Partnerships prison representative (usually DSLs) need to make the partners aware of what is happening in order to get wider system alignment and integration. So these roles have a vital strategic role to play in system design and delivery.

## Spectrum CIC evaluation (hidden)
Spectrum evaluation reccomendations
Buvidal should be provided as an OST option in all prisons as it provides patients with a choice regarding their OST medication, bringing care in line with community practice, and ensuring continuity of care as patients move between the community and prison, and transferred between prisons.
OST patients considering Buvidal as a treatment option should be given clear expectations, particularly around the potential discomfort they may experience whilst transferring from methadone to Buvidal, and the requirement to move to monthly dosing of Buvidal once stabilised on weekly injections
Care needs to be given to the language used with patients when introducing new treatment options within the prisons. Whilst Buvidal may be a new treatment that is being provided at these sites, it is not an investigational medicinal product and thus staff should avoid using terminology such as ‘trial’ or ‘pilot
Patients moving to Buvidal medication should be encouraged to engage in purposeful activity and, where required, be referred to mental health services for support in managing the negative effects of past trauma that may emerge from moving to a partial agonist medication
Peer-support/mutual-aid groups specific to Buvidal should be available in the prisons to help disseminate information about this new OST option and to provide a forum where patients on Buvidal can support one another.
Given that some patients may struggle to titrate their methadone to 30mg daily to be able to be moved to Buvidal, future research should explore the potential for switching to Buvidal from higher doses of methadone.
To ensure that Buvidal is a treatment option for all OST patients within prisons, healthcare services should work closely with their local commissioning teams to ensure that there is secured funding in place to enable this possibility. For commissioners, this may involve increasing the funding allocated to OST budgets for prison healthcare services
If caps on Buvidal patients are in place within prisons due to costing implications, clinical and non-clinical teams should be careful not to oversell the offer of Buvidal to patients as an inability or delays in being able to access Buvidal may have a detrimental impact on patients’ recovery journeys
Prison sites considering incorporating Buvidal as an OST treatment offer should take a collaborative approach to implementation, one that involves all key stakeholders
Buvidal training should be provided to all healthcare staff, not just those responsible for delivering substance misuse services within prisons. Consideration should also be given to offering face-to-face as well as online training.
To be comprehensive, Buvidal training for staff should incorporate how to undertake a Buvidal detoxification with a patient, and how to convert them back to methadone if this is their preference.
It is vitally important that prison healthcare services collaborate with their community drug treatment partners to ensure that community services are able and prepared to continue Buvidal provision for patients being released from prison.
Prison healthcare services considering implementing Buvidal at their respective sites should ensure that there is enough staff capacity to be able to initiate, monitor, and support patients that are moved to Buvidal
Buvidal Implementation in Secure Environments: a Service Evaluation of the Spectrum Community Health Pilot Sites Authors: Dr Pip Hearty, George Charlesworth, and Dr Nat Wright

## Buvidal Project Plan - GANTT (hidden)
BACKGROUND The following project planner has been designed to support drug treatment providers in mapping out and completing the relevant activities in order to implement Buvidal® prolonged release buprenorphine solution for injection into their local opioid dependence treatment systems. Please note, this project planner serves as a guide and cannot include all the specific local requirements that may need to be fulfilled. Some activities listed below and the sequence in which they are listed may be irrelevant depending on the organisation. Therefore, users are encouraged to make amendments to reflect their organisation’s individual requirements. It often helps to identify and engage with wider system stakeholders to ensure awareness of Buvidal and enable continuity of care.
Task Legend:
[8 empty] | On track |  |  |  |  | Delayed |  |  |  |  | Need help |  |  |  |  | Complete
[5 empty] | Gantt chart start date | 2025-02-24
A Scrolling Increment is in cell F5. Months for the dates in row 6 are displayed starting in cells H5 to cell BK5. Do not modify these cells. They are auto-updated based on the Gantt chart start date in cell F4. |  |  |  |  | Scroll bar increment | 0 |  | February | [6 empty] | March | [34 empty] | April
Cells H6 to BK6 contain the day number of the month for the Month represented in the cell block above each date cell and are auto-calculated. Do not modify these cells. Today’s date is outlined in Red (hex #AD3815) from today’s date in row 6 through the entire date column to the end of the project schedule. | time axis 2025-02-24 to 2025-04-20
A scrollbar is in cells H7 to BK7. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forwards or backwards in the timeline, enter a value of 0 or higher in cell E5. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B8 to BK8 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell H8 and continues to cell BK8. All project timeline charting is auto-generated based on the category, start date and number of days entered in the Milestones table. | Task | Owner | Considerations (please hover pointer over right side of considerations for examples) | Status | % Completion | Start date | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B10 to cell F10. Enter Milestone Description, select a Category from the drop-down list, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Engagement and buy-in from stakeholders
Buvidal presentation to Drug Treatment Service (DTS)/Commissioner to establish need to integrate Buvidal into the treatment pathway
DTS/Commissioner agrees to integrate Buvidal into the pathway
DTS/Commissioner to consult with relevant Pharmacy Lead and establish Controlled Drug (CD) license status of premises and to decide on Buvidal dispensing/delivery model i.e. Onsite, Buddy pharmacy or Pharmacist administration
DTS/Commissioner develops proposal/business case for implementing Buvidal including the financial impact and potential numbers of patients to receive Buvidal
Proposal/business case presented to relevant management team/stakeholder group and approval secured for implementation
Establish Buvidal implementation lead and/or multi-disciplinary working group with clinical and non-clinical representation
Formulary approval
Identify a clinician that will support the Buvidal formulary submission
Supporting clinician collates evidence required for the formulary submission
Buvidal submission discussed and reviewed at a relevant meeting (may commonly referred to as drugs and therapeutic committee meetings, formulary meetings, medicines management meetings etc)
Staff training and clinical protocol development
| All relevant staff receive training: (1) Buvidal presentation (safety profile and efficacy), (2) Buvidal administration including video demonstration and practice using demonstration devices (3) familiarisation with supporting materials i.e. patient information booklets, patient alert card, HCP information booklet, dosing card, quick injection guide |  |  | On Track |  | 15/07/21 | 7
Clinical protocol development: DTS determine their patient selection criteria
Clinical protocol development: DTS finalise their clinical protocol and other relevant SOPs
enter Project information starting in cell B10 to cell F10. Enter Milestone Description, select a Category from the drop-down list, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Clinical protocol development: documentation is signed of by relevant clinician/team
Initiating Buvidal
Keyworkers/ clinicians identify patients on their caseloads using the agreed patient selection criteria
Suitable patients are invited into a session where they are informed about Buvidal
Patients agreed to commence Buvidal are booked in to see the prescribing clinicians and psychosocial team
Prescribers liaise with their respective Pharmacy departments or local pharmacy to ensure that the correct dose/strength preparations of Buvidal is ordered in advance of patients commencing treatment
Patients to be booked in for prescribing review
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one
Note on AH3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We mentioned the categories during the last call, instead of removing do you think it would be helpful to rename. Ive reviewed a number of other templates and they have categories like, require help, waiting for signoff etc.?
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If opting for on-site model:- is a HO Licence required? is there a CD cabinet in place? is there an account with Alliance Healthcare in place? If opting for a buddy pharmacy model:- is there a CD cabinet in place? If opting for a Pharmacist administration model:- budget holder to agree tariff/contract with Pharmacist/s. does a Patient Specific Directive (PSD) need to be developed? what about indemnity insurance?
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Which patient groups? Which service/s and the hubs/locations/sites will Buvidal be available from? What's the timescale for implementation?
Note on D15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agree structure to support project governance and oversight
Note on D16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prescribing lead, nursing lead, operational/service lead, recovery team lead, pharmacy lead. For secure environments also consider representation from healthcare team, mental health team, on-call team, justice team. Schedule meetings to allow for actions to be agreed and progressed.
Note on D19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Which committee/s? What documentation is required? When does documentation need to be submitted and to who? When are submissions reviewed? Is someone able to/required to attend the committee meeting to present the case/respond to questions
Note on D22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Clinical staff - prescribers, nurses, pharmacists Non-clinical staff - operational/service manager, psychosocial team, prescribing administration Additional staff in secure environments - mental health team, justice team, on-call team, drug strategy lead, relevant governor
Note on D23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For secure environments:- Is medical hold necessary/appropriate?
Note on D24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Clinic rooms? Clinic time? Staff availability? Are computer system updates/changes required/helpful? If buddy pharmacy model is planned;- how will patient consent to medication being collected on their behalf be captured? how will prescriptions be delivered and collected from the pharmacy?
Note on D25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are there any other committees/management teams that need to be aware of protocol?

## Feedback Sheet (hidden)
Name | Comment
Martin

## Project worksheet (blank) (hidden)
| Phase 5 |  |  |  |  | Task Legend:
[6 empty] | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Complete
|  |  | Gantt chart start date | 2025-02-24
A Scrolling Increment is in cell F5. Months for the dates in row 6 are displayed starting in cells H5 to cell BK5. Do not modify these cells. They are auto-updated based on the Gantt chart start date in cell F4. |  |  | Scroll bar increment | 0 |  | February | [6 empty] | March | [34 empty] | April
Cells H6 to BK6 contain the day number of the month for the Month represented in the cell block above each date cell and are auto-calculated. Do not modify these cells. Today’s date is outlined in Red (hex #AD3815) from today’s date in row 6 through the entire date column to the end of the project schedule. | time axis 2025-02-24 to 2025-04-20
A scrollbar is in cells H7 to BK7. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forwards or backwards in the timeline, enter a value of 0 or higher in cell E5. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B8 to BK8 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell H8 and continues to cell BK8. All project timeline charting is auto-generated based on the category, start date and number of days entered in the Milestones table. | Title | Category | Progress % | Start date | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B10 to cell F10. Enter Milestone Description, select a Category from the drop-down list, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Objective 1
Task 1
Task 2
Task 3
Task 4
Objective 2
Task 1
Task 2
Task 3
Task 4
Task 5
Title 3
Task 1
Task 2
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one

## workdays (hidden)
Working days |  | Bank Holidays UK
Month | Working days | Date | Day | Holiday
2021-01-01 | 20 | 2021-01-01 | Friday | New Year's Day
2021-02-01 | 20 | 2021-04-02 | Friday | Good Friday
2021-03-01 | 23 | 2021-04-05 | Monday | Easter Monday
2021-04-01 | 20 | 2021-05-03 | Monday | Early May bank holiday
2021-05-01 | 19 | 2021-05-31 | Monday | Spring bank holiday
2021-06-01 | 22 | 2021-08-30 | Monday | Summer bank holiday
2021-07-01 | 22 | 2021-12-27 | Monday | Christmas Day (substitute day)
2021-08-01 | 21 | 2021-12-28 | Tuesday | Boxing Day (substitute day)
2021-09-01 | 22
2021-10-01 | 21
2021-11-01 | 22
2021-12-01 | 21
Formulas:
Working days = NETWORKDAYS([Month], EOMONTH([Month], 0), BankHolidays[Date])

## dropdowns (hidden)
Category
Objective
On Track
Low Risk
Med Risk
High Risk
Complete